## Slide 1: CoSMoS: Coupled Simulation and Modeling of Systems-on-Chips
IMS2003/RFIC2003
Project Overview
June 19, 2003
Notes: This is a sample presentation template

## Slide 2: Outline
Team
Objectives
CoSMoS structure
CoSMoS work
Accomplishments since last review
Milestones
EM simulation in CoSMoS
Pavel Nikitin
Vikram Jandhyala
Notes: This is the flow

## Slide 3: Team
University of Washington
  Professors: Richard Shi, Vikram Jandhyala, David Allstot, Carl Sechen
  Postdoctoral researchers: Guoyong Shi, Pavel Nikitin
  Ph.D. students: Bo Wan, Bo Hu, Sam Bhattacharya, Zhao Li, Nuttorn Jangkrajarng, Lei Yang, Lili Zhou, Renpi Yu, Yong Wang, Dipanjan Gope,Todd West, Swagato Chakraborty, Chuanyi Yang
Lawrence Livermore National Laboratory
  Rob Sharpe, Dan White, John Rockway
Space and Naval Warfare Systems Command
  John Rockway
Boeing Solid State Electronics
Orora Design Technologies

## Slide 4: Objectives
Develop modeling and simulation capability for mixed-signal and mixed-technology systems
Achieve significant simulation speed improvement
Realize “device model in a day” concept using a behavioral model compiler
Develop accurate EM tools for coupled systems
Extend VHDL-AMS to mixed-technology
Validate tools on realistic DoD designs

## Slide 5: CoSMoS Structure

## Slide 6: BMAC (MCAST): VHDL-AMS model compiler
Supports industry-grade transistor models and mixed-technology
Plugs into commercial circuit simulator

## Slide 7: VHDL-AMS work
Background on VHDL-AMS
  IEEE 1076.1 behavioral language standard
  Suitable for time domain simulation of mixed circuits and simple multiple physics via DAE’s
  Provides a hierarchical system description independent of solving method
  Systems can have different nature
Practical language extension is needed for:
  Mixed technology support (distributed interactions)
  Easy model exchange between designers

## Slide 8: IPRAIL
Template-Driven Analog Layout Retargeting
Analog Layout
in Tech1
Analog Layout
in Tech2
Tech 1
Tech 2
New Specification
Symmetry
Reuse previous RF/analog design to do resizing for new technology

## Slide 9: FROSTY
Create gate-level netlist from extracted netlist

## Slide 10: Other Research
Linear solver research
Nonlinear time-domain solver research (SILCA)
Symbolic delay estimation in digital circuits with parasitics (SAMBA)

## Slide 11: Accomplishments Since Last Review
Finished implementation of transistor models: BSIM3, SOI, EKV
Mixed-technology support in BMAC
CoSMoS tools demo and test installation and Boeing
FROSTY and IPRAIL development and verification

## Slide 12: Milestones
July 2003
  BMAC release at AFRL
August 2003
  VHDL-AMS mixed-technology examples
September 2003
  Frequency domain support in BMAC
  Frequency domain CoSMoS simulator prototype
December 2003
  Digital support in BMAC
  Time domain CoSMoS simulator prototype
  Technology transfer to Boeing (BMAC, IPRAIL, FROSTY)
June 2004
  Final release of tools

## Slide 13: EM Simulation in CoSMOS
Personnel
  EM Lead Prof. Vikram Jandhyala UW
  Dr. Robert Sharpe, Dr. Daniel White, Dr. Nathan Champagne LLNL
  Swagato Chakraborty, Dipanjan Gope (NSF-SRC), Gong Ouyang, Todd West, Yong Wang (NSF-SRC), Chuanyi Yang (NSF) UW
  Liaisons to Circuit Simulation Work – Dr. Pavel Nikitin, Todd West, Yong Wang UW

## Slide 14: Essential Formulation : Coupled EM and Circuit Simulation in Time and Frequency Domains : Hierarchical / Telescoping Approach
Realistic circuit coupling applications and visualization/design of
circuit effects on EM simulation
Vpeak: 10mV
Vbias
Vbias
inp
inm
outp
outm
L1
L2
L3
L4
L5
L6
2.5V
Itail
Decoupling capacitors : A/D/RF
LNA: Mutual inductance effects
Y. Wang

## Slide 15: UW EM Status
General multi-region formulation including exact loss effects, volumetric models, and effective surface impedance
  Completed on schedule
  On track for December 2003 deliverable of multi-region solver
Green's function-independent QR fast iterative and direct solver
  Iterative solver completed (improves over existing commercial solvers) on schedule
  On track for fast direct solver completion for December 2003
Well-conditioned, multi-frequency fast multipole method
  Initial FMM implementation in EM prototype code completed
  Need further testing and optimization for July 2003 completion on schedule
Integration of EM Model Order Reduction into CoSMoS
  AWE based methodology transferred to EIGER, implemented in EIGER on schedule
  Other NeoCAD MOR schemes – PRIME : No response/progress
Time domain integral equation (TDIE) with exact circuit coupling
  Stand-alone prototype solver completed ahead of schedule
  Additional work on stability, accuracy completed
Fast solver and time stepper for Time domain integral equation (TDIE)
  Not completed

## Slide 16: LLNL-UW EM Status
EIGER : Frequency Domain EM
  Neutral File Format – interface for using any commercial mesher : Completed on schedule, delivered to UW
  Stand-alone multilayered Green’s function interface : Delivered to UW for prototype testing of fast solvers
  Incorporation of MOR-AWE into EIGER : Completed ahead of schedule
  Contact model generation : Completed on schedule
EMSolve : Time Domain EM
  Interface to CFDRC Micromesh completed
  Fast static solver completed
  Running of test cases completed

## Slide 17: EMSolve
source
sensor
  coplanar waveguide
  spiral inductor
  IEEE benchmark
  UW VCO
D. White

## Slide 18: UW EM Parasitic Extraction (completed)
ic_hrl_tc1
0.1 million patches
6 RHS solutions
Algorithm | Memory | Time
UW Parasitic Solver | 365MB | 19min
(Cadence / Lucent IES3) | 380MB | 27min
FAST-CAP/ Ansoft Q3D | 500MB | 30min
D. Gope and V. Jandhyala

## Slide 19: Parasitics in massively coupled problems (completed)
Algorithm | Memory | Setup | Solve (3RHS)
UW Parasitic Solver | 3.3GB | 48min | 49min
IES^3 | Could Not Fit in Memory |  | 
FASTCAP / Ansoft Q3D | Could Not Fit in Memory |  | 
UW EM parasitic solver : 0.9 million patches in 1.5 hours!
D. Gope and V. Jandhyala
Faster than commercial solvers, Green’s function independent

## Slide 20: Broadband Full-Wave Parasitic Extraction (completed)
0.6%
0.1%
Commercial Solver Comparisons
Inductance
Resistance
S. Chakraborty and V. Jandhyala
Skin and Volume Effects
Not available in commercial surface-based solvers

## Slide 21: Adaptive Fast Multipole Method for Realistic Geometries with Arbitrary Aspect Ratio Elements
T. West and V. Jandhyala
Existing FMMs do not completely address this problem

## Slide 22: Direct Time Domain EM Simulation
Interconnect-Substrate Effects
C. Yang, G. Ouyang, and V. Jandhyala

## Slide 23: Coupled Circuit-EM Simulation in the Time Domain
The ACES IEEE/EMC Society TC9 2001 Challenge Problem-Find:Voltage
Between Line+ and CM Ground Point On Plane
C. Yang, G. Ouyang, and V. Jandhyala

## Slide 24
Stabilization of UW EM TDIE : Eigenvalue Analysis
C. Yang, G. Ouyang, and V. Jandhyala

## Slide 25: Summary of EM Progress
EIGER and EMSolve
  Incorporation of AWE, contact models
  Development of Neutral file interface
  Multi-physics capable (EMSolve and UW EM TDIE to work in conjunction) for device layer effects
UW EM Frequency Domain Prototype
  Coupling to SPICE-like code
  Fast solvers (FMM and QR-based)
  Multi-region formulations and lossy material models
  Fast frequency sweep / Integrated MOR
  Interface from commercial meshers
  Can be driven from Matlab
UW EM Time Domain Prototype
  Coupling to SPICE-like code
  Stability analysis and enhancements
  Material modeling
  Extensible to EMI/EMC and device/multi-physics coupling