## Sheet1
Job Function | Owner | Start | Finish |  | Remark
I. Migrating Phase |  | 2003-01-03 | 2003-01-31
Goal: Extracting and Regenerate the layouts in SOI process with the original and make-up size of transistors and inductors
Via insertion | Nuttorn | 2003-01-03 | 2003-01-10 | OK
Inductor port connection | Roy | 2003-01-03 | 2003-01-10 | OK
Update sweepline function so it includes '0' '-1' constraint and other items about design rules | Both | 2003-01-10 | 2003-01-17 | OK
Loading the VCO layout | Nuttorn | 2003-01-03 | 2003-01-24 | OK | Working concurrently with other part
Textual reading of transistor size (as fingered numbering) | Roy | 2003-01-17 | 2003-01-24 | Dropped | No need to be perfect b/c it wil be changed again after optimizer
Checking the transistor size for un-conformality with symmetry and fingering | Roy | 2003-01-17 | 2003-01-24 | OK
Capacitor and Resistor | Roy | 2003-01-17 | 2003-01-31 | OK
Resizing the VCO layout | Nuttorn | 2003-01-24 | 2003-01-31 | * | OVERDUE
Problems in wlm | Nuttorn |  | 2003-01-31 |  | Only if time left (actually, it's necessary for the result!!! > Find time for it)
II. First Optimizer Phase |  | 2003-01-31 | 2003-02-14
Goal: Running the VCO layout (and ADC if ready) with optimizer on the transistor sizing. Also obtain and ready for CMOS5 (boeing design) resizing.
Enforcing symmetry into optimizer constraint | Nuttorn | 2003-01-31 | 2003-02-07
Variables tracking | ? | 2003-01-31 | 2003-02-07
Obtain and test technology file of CMOS5 | Both | 2003-01-31 | 2003-02-07
Obtain Arsyn | ? | 2003-01-31 | 2003-02-07 |  | Only if testing of VCO/ADC is possible
Input and output interface with optimization tool | Roy | 2003-02-07 | 2003-02-14
Testing the VCO | Both | 2003-02-07 | 2003-02-14
Testing the ADC | Nuttorn | 2003-02-07 | 2003-02-14
Detecting positive cycle | Nuttorn |  |  |  | Only if time left
Checking complexity | Nuttorn |  |  |  | Only if time left
Job Function | Owner | Start | Finish |  | Remark
III. Parasitic Extraction Phase |  | 2003-02-14 | 2003-02-28
Goal: Extract and generate the parasitic res/cap values and verify the simulation result of parasitic-netlist
Update with Sam | Nuttorn | 2003-01-24 | 2003-02-21
Correcting the hard-coded device layer definition | Roy | 2003-02-14 | 2003-02-21
RC model and constraint generation of wire | Nuttorn | 2003-02-14 | 2003-02-21
Simulate the generated netlist and other netlist | Nuttorn | 2003-02-21 | 2003-02-28
IV. Parasitic Constraint Evaluation Phase |  | 2003-03-07 | 2003-03-21
Goal: Parasitic constraints are suitable for optimization and result is suitable for the resizer
V. Optimization and Summary |  | 2003-03-21 | 2003-04-04
Goal: Running the circuit with optimizer tool and test/verify the
Test the VCO for the whole process |  | 2003-03-21 | 2003-03-28
Test the ADC for the whole process |  | 2003-03-21 | 2003-03-28
Extra.
Goal: Items needed
Technology file CMOS5
Simulation of the layout ADC
Simulation of the layout VCO
Parasitic problem understading
Note.
The overdue items are in RED.
The next two-weeks items are in GREEN.